## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | JOB CLOUD
PROJECT ID
PROJECT MANAGER | JAYANTH G S
PROJECT SPONSOR | CLOUD COUNSELAGE PVT LTD
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-03-07 | Dataset file corrupted | TECHNICAL | Unable to read csv | Save file with proper encoding | Rectified encoding | Rahil Merchant | CLOSED
| 20/7/2020 | Wrong Scaler used | TECHNICAL | Unusual F1 score | Use appropriate scaler | Used standard scaler | Rahil Merchant | CLOSED
| 25/7/2020 | Visualization getting cut in PDF | TECHNICAL | none | Use a smaller figsize value for pdfs | Resized vizualizations | Rahil Merchant | CLOSED
| 26/7/2020 | PDF merge not working | TECHNICAL | none | Use different library | Used different library | Rahil Merchant | CLOSED
| 29/7/2021 | Unable to take command line input | TECHNICAL | none | Use sys.arg[] instead of input() function | Used sys library to get command line argument of dataset | Rahil Merchant | CLOSED