## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | IP Data Science Live Project
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-04-07
PROJECT DELIVERABLE |  |  | EXECUTION PHASE END DATE: |  | 31/7/20
PROJECT SCOPE
PROJECT START DATE
PROJECT END DATE
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
Initiation | 1.1 Understanding SDLC | 6 | 15/6/2020 | 17/6/2020 | 3 | COMPLETED
| 1.2 Identify business problem | 6 | 18/6/2020 | 20/6/2020 | 3 | COMPLETED
| 1.3 Requirement gathering | 6 | 20/6/2020 | 22/6/2020 | 3 | COMPLETED
| 1.4 Creating project charter | 4 | 24/6/2020 | 24/6/2020 | 1
Planning | 2.1 Creating Design Model | 4 | 25/6/2020 | 25/6/2020 | 1 | COMPLETED
| 2.2 Creating SRS | 4 | 28/6/2020 | 28/6/2020 | 1 | COMPLETED
| 2.3 Baseline Project Plan | 6 | 30/6/2020 | 2020-02-07 | 3 | COMPLETED
Execution | 3.1 Data Cleansing | 6 | 2020-02-07 | 2020-04-07 | 3 | COMPLETED
| 3.2 Encoding categorical values | 6 | 2020-06-07 | 2020-06-07 | 1 | COMPLETED
| 3.3 Build Data Visualizations to plot | 36 | 2020-10-07 | 20/7/2020 | 11 | COMPLETED
| 3.4 Build binary classifier to classify data into eligible and not eligible | 36 | 21/7/2020 | 31/7/2020 | 11 | COMPLETED
Closure | 4.1 Creating Detailed Project Report | 6 | 29/7/2020 | 31/7/2020 | 3 | COMPLETED